## Workbook Notes
Workbook Notes
Item | Description
Purpose | This workbook is the dynamic implementation tracker for comparing current Redmine dashboard pages with the Target Dashboard Design.
Design Baseline | The Word document and Metrics Excel define the stable Target Dashboard Design. This workbook may change as implementation evolves.
Rule | Do not delete existing Redmine tabs automatically. Reuse, rename, reposition, or keep them as supporting/detail tabs where appropriate.
Current Redmine Tabs from Screenshot | PMO Control; Sprint Delivery; Planning & Estimation; Duration Report; Issue Detail; Ticket Owner Performance; QA & Returns; Owner Workload; Aging / SLA Risk; Priority / SLA Risk; Cycle Distribution; Flow Report; Project Health; Release Readiness; Bugs Analysis; Data Quality
Target Dashboard Sections | PMO Control Dashboard; Sprint Delivery Dashboard; Team / Ticket Owner Performance Dashboard; QA & Returns Dashboard; Bug Control Dashboard; Planning & Estimation Dashboard; Ticket Quality & Data Discipline Dashboard; Time Utilization & Scope Control Dashboard

## PMO Dashboards Implementation
V14 Redmine Dashboard Mapping Matrix
Main Target Dashboard Tab | Supporting / Detail Tabs to Keep Under This Section | Current Redmine Tabs to Reuse | Present in Redmine? | Comment | Expected Tables / Reports from Target Dashboard | Remaining Tables to Implement / Confirm | Status / Developer Note
PMO Control Dashboard | PMO Control | Project Health Release Readiness Aging / SLA Risk Priority / SLA Risk Issue Detail | Yes | T01 — Open Technical Tickets Snapshot T02 — Cross-Project Risk Summary T03 — Open Tasks / Business Jobs T04 — Open Milestones T44 — Feature / Improvement Visibility by Version or Date | PMO Control Project Health Release Readiness Aging / SLA Risk Priority / SLA Risk Issue Detail | Confirm all T01-T04 and T44 exist with required filters and drill-down. Confirm risk summary does not duplicate Project Health as a second source of truth. | Keep PMO Control as the main executive control tab. Use supporting tabs only as detail/risk views.
Sprint Delivery Dashboard | Sprint Delivery | Duration Report Cycle Distribution Flow Report Priority / SLA Risk Issue Detail | Yes | T05 — Committed Tickets for Sprint #X T06 — Sprint Tasks Distribution in Statuses T07 — Sprint Execution Efficiency / Original Sprint Composition T08 — Sprint Completion Summary T09 — Done Tickets Time Efficiency T10 — Ticket Status Change Trend T11 — Tracker Change Trend T12 — High-Priority Delivery View T45 — Daily Agile Board Snapshot | Sprint Delivery Duration Report Cycle Distribution Flow Report Priority / SLA Risk Issue Detail | Confirm retrospective committed-ticket baseline, sprint snapshot logic, status distribution, high-priority delivery, and daily board snapshot are implemented. | Keep Sprint Delivery as the main sprint execution tab. Supporting tabs should help explain duration, flow, and risk.
Team / Ticket Owner Performance Dashboard | Ticket Owner Performance | Owner Workload Duration Report Issue Detail | Yes, with different Redmine label | T13 — Ticket Delivery Analysis by Owner T14 — Done Committed Tickets Analysis by Owner T15 — Average Time for Each Status T16 — Owner Ticket Idle / No Update Detail T17 — Owner Time Allocation | Ticket Owner Performance Owner Workload Duration Report Issue Detail | Confirm owner performance is balanced and not only based on completed ticket count. Confirm T17 is treated as secondary/cross-view and aligns with T42. | Keep current Redmine tab name if needed, but map it clearly to Team / Ticket Owner Performance Dashboard.
QA & Returns Dashboard | QA & Returns | Flow Report Issue Detail | Yes | T18 — Done Tickets Analysis T19 — Returned Tickets Analysis — Count T20 — Returned Tickets Analysis — Duration T21 — Work & Rework Ratio T22 — Return Reason Analysis | QA & Returns Flow Report Issue Detail | Confirm returns and bugs are not mixed. Confirm return reason, return count, return duration, and rework logic are captured. | Keep QA & Returns as the main internal quality and return-loop tab.
Bug Control Dashboard | Bugs Analysis | Aging / SLA Risk Priority / SLA Risk Release Readiness Issue Detail | Yes, with different Redmine label | T23 — Bugs Analysis by Category T24 — Bug Impact Summary T25 — Related Page Histogram T26 — Critical Bugs Open Detail | Bugs Analysis Aging / SLA Risk Priority / SLA Risk Release Readiness Issue Detail | Confirm current Bugs Analysis tab covers Target Bug Control Dashboard requirements. Keep target terminology as Bug Control Dashboard; current Redmine tab can remain Bugs Analysis. | Keep Bugs Analysis as current Redmine tab unless renaming is practical. Map it to Bug Control Dashboard.
Planning & Estimation Dashboard | Planning & Estimation | Duration Report Owner Workload Issue Detail | Yes | T27 — Planning vs Actual Time Analysis T28 — PM Estimation vs Owner Estimation vs Time Spent T29 — Original Sprint Composition T30 — Open Planned Tickets Health T31 — Not Started Tickets T32 — Commitment Reliability Summary T33 — Carry-over Reason Analysis | Planning & Estimation Duration Report Owner Workload Issue Detail | Confirm PM estimation, owner estimation, actual time spent, not-started work, original sprint composition, and carry-over reason are available. | Keep Planning & Estimation as main planning-control tab.
Ticket Quality & Data Discipline Dashboard | Data Quality | Issue Detail | Yes, with different Redmine label | T34 — Open Planned Tickets Health T35 — Tickets Without Updates T36 — Missing Required Fields Detail T37 — Data Reliability by Project | Data Quality Issue Detail | Confirm Data Quality covers missing required fields, tickets without updates, open planned tickets health, and reliability by project. | Keep current Redmine tab name if needed, but map it clearly to Ticket Quality & Data Discipline Dashboard.
Time Utilization & Scope Control Dashboard | No exact current Redmine main tab | Owner Workload Duration Report Issue Detail | Missing as direct tab / partially supported | T38 — Spent Time: General vs Sprint Tickets T39 — Out-of-Sprint Scope Works T40 — Spent Time on Group of Tickets in Specific Date Period T41 — Average Spent Time vs Calendar Duration T42 — Owner Time Allocation T43 — Activity Distribution in Spent Time Report | Owner Workload Duration Report Issue Detail | Either add a direct Time Utilization & Scope Control tab or explicitly place T38-T43 under Owner Workload / Duration Report / Issue Detail with clear ownership. | Recommended: add Time Utilization & Scope Control as a main tab if feasible. Otherwise document exact hosting location for T38-T43.

## Supporting Tabs Reference
Mapping of Current Implemented Tabs to the Final Design (V14-Names Checked)
Current Redmine Tab | Tab Type | Recommended Target Section(s) | Role in Target Design | Developer Note | Keep / Rename / Reposition
PMO Control | Main | PMO Control Dashboard | Main executive control dashboard. | Should remain the main source of truth for executive project/sprint health, risks, blockers, bugs, ticket quality, and time-utilization signals. | Keep as main tab
Sprint Delivery | Main | Sprint Delivery Dashboard | Main sprint execution dashboard. | Should contain sprint commitment, completion, carry-over, status distribution, high-priority delivery, and daily board snapshot. | Keep as main tab
Planning & Estimation | Main | Planning & Estimation Dashboard | Main planning-control dashboard. | Should include estimation accuracy, commitment reliability, not-started work, original sprint composition, and carry-over reason analysis. | Keep as main tab
Ticket Owner Performance | Main | Team / Ticket Owner Performance Dashboard | Main owner-level performance dashboard. | Current Redmine name is acceptable. It should evaluate owners with balanced signals, not only completed ticket count. | Keep; target mapping name differs
QA & Returns | Main | QA & Returns Dashboard | Main internal quality and return-loop dashboard. | Should separate returns from bugs and include return count, duration, rework ratio, and return reason analysis. | Keep as main tab
Bugs Analysis | Main | Bug Control Dashboard | Current Redmine implementation of the target bug-control view. | Current tab name is Bugs Analysis, but target design name is Bug Control Dashboard. Ensure T23-T26 are covered. | Keep or optionally rename later
Data Quality | Main | Ticket Quality & Data Discipline Dashboard | Current Redmine implementation of ticket-quality and data-discipline view. | Current tab name is Data Quality, but target design name is Ticket Quality & Data Discipline Dashboard. Ensure T34-T37 are covered. | Keep or optionally rename later
Duration Report | Supporting | Sprint Delivery Dashboard Team / Ticket Owner Performance Dashboard Planning & Estimation Dashboard Time Utilization & Scope Control Dashboard | Duration, cycle-time, lead-time, status-duration, and spent-time support view. | Should contain cycle time, lead time, time in status, blocked duration, overdue duration, and spent time vs calendar duration. | Keep as supporting/detail tab
Issue Detail | Supporting / Drill-down | All target dashboard sections | Shared ticket-level drill-down layer. | Should support filtering by project, sprint, original sprint, owner, tracker, status, priority, dates, return reason, bug source, time log, and activity. | Keep as shared drill-down tab
Owner Workload | Supporting | Team / Ticket Owner Performance Dashboard Time Utilization & Scope Control Dashboard Planning & Estimation Dashboard | Owner workload, effort allocation, sprint vs non-sprint work, and capacity/planning support view. | Useful, but it should not replace the full Time Utilization & Scope Control dashboard unless all T38-T43 are included. | Keep as supporting tab
Aging / SLA Risk | Supporting | PMO Control Dashboard Bug Control Dashboard Sprint Delivery Dashboard | Aging, SLA, overdue, and unresolved-risk support view. | Should include overdue duration, aging unresolved items, open critical bug aging, SLA risk, blocked/idle aging, and high-risk unresolved tickets. | Keep as risk/supporting tab
Priority / SLA Risk | Supporting | PMO Control Dashboard Sprint Delivery Dashboard Bug Control Dashboard | Priority-based and SLA-based risk control view. | Should focus on high-priority delivery, high-priority cycle time, urgent/hotfix tickets, critical bugs, delayed priority items, and SLA breaches. | Keep as risk/supporting tab
Cycle Distribution | Supporting | Sprint Delivery Dashboard Team / Ticket Owner Performance Dashboard Time Utilization & Scope Control Dashboard | Cycle-time distribution and delivery-speed analysis. | Should show cycle-time distribution by ticket, owner, priority, tracker, sprint, and possibly complexity. | Keep as analytical support tab
Flow Report | Supporting | Sprint Delivery Dashboard QA & Returns Dashboard Time Utilization & Scope Control Dashboard | Workflow movement, status transition, return-flow, and bottleneck analysis. | Should include ticket status movement, tracker movement, bottleneck behavior, time in status, returned-flow behavior, and flow trend. | Keep as flow-analysis tab
Project Health | Supporting | PMO Control Dashboard | PMO summary / health sub-view. | Should not duplicate PMO Control as a second source of truth. Use as a project-health summary view. | Keep as supporting PMO summary tab
Release Readiness | Supporting | PMO Control Dashboard Bug Control Dashboard | Release-risk and readiness support view. | Useful as a management tab. Should include critical bugs, testing coverage, release blockers, readiness score, and release risk signals. | Keep as supporting management tab