## Categories and Goals
Category | What it Measures | Goal
Delivery Health | Output, completion, predictability | Measure whether the team is delivering planned scope on time, meeting sprint commitments, progressing toward milestones, and controlling unfinished committed work.
Execution Efficiency | Time usage, workflow movement, bottlenecks, and logged effort distribution | Measure how efficiently time is utilized, how work flows through the system, where bottlenecks exist, and how logged effort is distributed.
Quality & Returns | Internal defects, returns, and rework | Measure how often work is completed correctly and identify return, rework, and internal quality patterns.
Bug Intelligence | Bug lifecycle, bug source, severity, and production impact | Analyze bug trends, root causes, impact, leakage, and resolution effectiveness.
Planning & Estimation Discipline | Planning accuracy, estimation reliability, commitment realism, and carry-over causes | Evaluate planning accuracy, estimation reliability, commitment realism, out-of-sprint work, carry-over causes, and execution alignment with planning assumptions.
Release Readiness | Go/No-Go signals and release risk | Assess whether the system is ready for release with acceptable risk.
Ticket Quality | Data reliability and ticket completeness | Ensure ticket data is complete, updated, accurate, and reliable for planning and dashboard analysis.

## PMO Dashboard_Metrics_V14HA
Metric No. | Category | Type | Metric | Definition & Explanation | Phase | Formula | Frequency | Owner | Target | Action | KPI Flag | Source Data | Notes how to Extract from Redmine
1 | Delivery Health | Core | Completed Committed Tickets | Committed sprint tickets completed within sprint | Phase 1 | COUNT(committed AND closed within sprint) | Sprint | PM | Trend ↑ | Review planning/blockers | TRUE | Sprint baseline, status | Use sprint snapshot + Done/Closed
2 | Delivery Health | Core | Sprint Completion Rate (%) | % of committed tickets delivered | Phase 1 | Completed Committed / Planned * 100 | Sprint | PM | ≥90% | Improve planning | TRUE | Sprint baseline | Committed vs closed
3 | Delivery Health | Core | Planned Tickets | Total committed sprint tickets | Phase 1 | COUNT(committed tickets) | Sprint | PM | Stable | Control scope | FALSE | Sprint baseline | Snapshot at sprint start
4 | Delivery Health | Core | Carry-over (%) | % of committed tickets not delivered | Phase 1 | COUNT(Original Sprint = Sprint X AND Status != Done/Closed at Sprint End) / Planned Tickets * 100 | Sprint | PM | <10% | Investigate delays | TRUE | Sprint baseline, status | Use Original Sprint as the commitment baseline. Do not use current sprint relation after tickets are moved.
5 | Delivery Health | Supporting | Carry-over Trend | Trend of carry-over over sprints | Phase 2 | TREND(Carry-over %) | Sprint | PM | ↓ | Improve stability | FALSE | Historical | Time series
6 | Delivery Health | Core | Throughput | Total completed tickets | Phase 1 | COUNT(closed tickets) | Sprint | PM | Stable/↑ | Check flow | TRUE | Status | Filter Done/Closed
7 | Delivery Health | Supporting | Delivery Predictability (%) | Stability of delivery performance | Phase 2 | STDDEV(Delivered/Planned) | Sprint | PM | Low variance | Improve planning | FALSE | Historical | Multi-sprint comparison
8 | Delivery Health | Supporting | Milestone Deliverables | Total milestone tickets | Phase 2 | COUNT(milestone tickets) | Release | PM | Defined | Validate scope | FALSE | Milestone field | Filter milestone
9 | Delivery Health | Analytical | Milestone Completion (%) | % milestone delivered | Phase 3 | Completed / Total * 100 | Release | PM | ≥95% | Check readiness | FALSE | Milestone, status | Closed tickets
10 | Delivery Health | Indicator | Sprint Status | Sprint health indicator | Phase 1 | IF Completion≥90% AND Carry-over<10% | Sprint | PM | On Track | Escalate | FALSE | Sprint metrics | Derived
11 | Execution Efficiency | Core | Cycle Time | Time from In Progress to Done | Phase 1 | AVG(close - first In Progress) | Daily | Dev Lead | ↓ | Improve flow | TRUE | Status logs | Track transitions
12 | Execution Efficiency | Core | Lead Time | Time from creation to completion | Phase 2 | AVG(close - created) | Daily | PM | ↓ | Improve intake | FALSE | Timestamps | Use created/closed
13 | Execution Efficiency | Core | Blocked Tickets Count | Blocked tickets count | Phase 1 | COUNT(status=Blocked) | Daily | Dev Lead | 0 | Escalate | TRUE | Status | Filter blocked
14 | Execution Efficiency | Core | Blocked Duration | Time tickets remain blocked | Phase 1 | AVG(blocked duration) | Daily | Dev Lead | ↓ | Resolve blockers | FALSE | Status logs | Measure duration
15 | Execution Efficiency | Core | Ticket Idle Time | Time since last activity | Phase 1 | NOW - last update | Daily | PMO | < threshold | Follow up | TRUE | Last updated | Use latest activity
16 | Execution Efficiency | Supporting | Overdue Tickets | Tickets past due date | Phase 2 | COUNT(due<today AND open) | Daily | PM | 0 | Reprioritize | TRUE | Due date | Filter overdue
17 | Execution Efficiency | Supporting | Overdue Duration | Total overdue time | Phase 2 | SUM(today - due) | Daily | PM | ↓ | Fix delays | FALSE | Due date | Aggregate
18 | Execution Efficiency | Supporting | Time in Status | Time per workflow stage | Phase 2 | SUM(duration per status) | Sprint | PMO | N/A | Find bottlenecks | FALSE | Status logs | Aggregate transitions
19 | Execution Efficiency | Supporting | Integration Time | Time in merge/integration stage | Phase 2 | SUM(integration duration) | Sprint | Dev Lead | ↓ | Improve merge | FALSE | Status logs | Filter stage
20 | Execution Efficiency | Supporting | Active Dev Time | Time in dev states | Phase 2 | SUM(dev states duration) | Sprint | Dev Lead | ↓ | Improve efficiency | FALSE | Status logs | Filter states
21 | Execution Efficiency | Supporting | Avg Dev Time per Ticket | Average dev effort | Phase 2 | Total dev time / tickets | Sprint | Dev Lead | ↓ | Improve performance | FALSE | Time logs | Aggregate
22 | Execution Efficiency | Supporting | Tickets Stuck in Status | Stale tickets count | Phase 2 | COUNT(duration>threshold) | Daily | PMO | 0 | Review flow | FALSE | Status logs | Compare duration
23 | Execution Efficiency | Analytical | Work-in-Progress (WIP) | Active work items | Phase 3 | COUNT(active tickets) | Daily | Team Lead | Limited | Reduce overload | FALSE | Status | Filter active
24 | Execution Efficiency | Analytical | Bottleneck Stage | Longest workflow stage | Phase 3 | MAX(time per status) | Sprint | PMO | N/A | Improve stage | FALSE | Status logs | Compare durations
25 | Quality & Returns | Core | Return Rate (%) | Tickets with returns | Phase 1 | Returned / total *100 | Sprint | QA | <15% | Improve quality | TRUE | Status transitions | Count Returned
26 | Quality & Returns | Supporting | Returns per Ticket | Return count per ticket | Phase 2 | COUNT(Return events) | Sprint | QA | ↓ | Review tickets | FALSE | Status logs | Count transitions
27 | Quality & Returns | Supporting | Avg Returns per Ticket | Average returns | Phase 2 | SUM(returns)/tickets | Sprint | QA | ↓ | Improve QA | FALSE | Status logs | Aggregate
28 | Quality & Returns | Analytical | Return Loop Depth | Max return cycles | Phase 3 | MAX(return count) | Sprint | QA | Low | Review unstable | FALSE | Status logs | Max loops
29 | Quality & Returns | Analytical | Return Cycle Duration | Time per return cycle | Phase 3 | AVG(return→next state) | Sprint | QA | ↓ | Improve speed | FALSE | Status logs | Measure transitions
30 | Quality & Returns | Supporting | Return-Induced Dev Time | Time after returns | Phase 2 | SUM(time after return) | Sprint | QA | ↓ | Reduce rework | FALSE | Time logs | Filter logs
31 | Quality & Returns | Core | Rework Ratio (%) | Rework share | Phase 1 | Rework / total dev *100 | Sprint | QA | <20% | Improve quality | TRUE | Time logs | Derived
32 | Quality & Returns | Core | Total Rework Time | Rework hours | Phase 1 | SUM(rework time) | Sprint | QA | ↓ | Reduce rework | TRUE | Time logs | Sum
33 | Quality & Returns | Core | First-Time Pass Rate (%) | No-return tickets | Phase 1 | No-return / total *100 | Sprint | QA | >80% | Improve quality | TRUE | Return data | Filter return=0
34 | Quality & Returns | Supporting | QA Fail Rate (%) | QA rejection | Phase 2 | QA fail / reviewed | Sprint | QA | ↓ | Improve QA | FALSE | Status logs | Feedback loop
35 | Quality & Returns | Supporting | Validation Rejection Rate (%) | Validation rejection | Phase 2 | Rejected / validated | Sprint | QA | ↓ | Improve validation | FALSE | Status logs | Validation stage
36 | Quality & Returns | Analytical | High-return Tickets | High rework tickets | Phase 3 | COUNT(return>threshold) | Sprint | QA | 0 | Review | FALSE | Return count | Filter
37 | Quality & Returns | Supporting | Return Trend | Return trend | Phase 2 | TREND(Return Rate) | Sprint | QA | ↓ | Improve quality | FALSE | Historical | Time series
38 | Quality & Returns | Supporting | Return Reasons Distribution | Return causes | Phase 2 | COUNT by type | Sprint | QA | N/A | Fix root cause | FALSE | Return type | Segment by severity groups: - Dev Issue: Wrong Implementation, Code Quality, Side Effect - Requirement Issue: Missed Requirement - System Issue: Data/Environment - Process Issue: Merge Conflict, Out-of-Scope
39 | Quality & Returns | Analytical | Return-based Fail Rate (%) | Return-driven failure | Phase 3 | Return failures / total | Sprint | QA | ↓ | Improve quality | FALSE | Return data | Derived
40 | Bug Intelligence | Core | Bugs Created | New bugs | Phase 1 | COUNT(created) | Weekly | QA | ↓ | Improve quality | TRUE | Tracker=Bug | Filter
41 | Bug Intelligence | Core | Bugs Resolved | Closed bugs | Phase 1 | COUNT(closed) | Weekly | QA | ↑ | Improve speed | TRUE | Status | Filter closed
42 | Bug Intelligence | Supporting | Bug Backlog Trend | Open bugs trend | Phase 2 | TREND(open bugs) | Sprint | QA | ↓ | Reduce backlog | FALSE | Status | Time series
43 | Bug Intelligence | Core | Bug Leakage (%) | Escaped bugs | Phase 1 | Escaped / total *100 | Sprint | QA | <5% | Improve QA | TRUE | Release tags | Segment by Bug Source: - Test Escape - Coverage Gap - Requirement Gap
44 | Bug Intelligence | Supporting | Bug Reopen Rate | Reopened bugs | Phase 2 | Reopened / closed *100 | Sprint | QA | ↓ | Improve quality | FALSE | Status logs | Track reopen
45 | Bug Intelligence | Supporting | Severity Distribution | Bugs by severity | Phase 2 | COUNT by severity | Sprint | QA | N/A | Prioritize | FALSE | Severity | Group
46 | Bug Intelligence | Core | Critical Bugs Open | Open critical bugs | Phase 1 | COUNT(critical open) | Daily | QA | 0 | Block release | TRUE | Severity | Filter
47 | Bug Intelligence | Analytical | Open Critical Bug Aging | Critical bug age | Phase 3 | AVG(today - created) | Daily | QA | Low | Escalate | FALSE | Timestamps | Calculate
48 | Bug Intelligence | Analytical | Resolution Time by Severity | Fix time per severity | Phase 3 | AVG(close-created by severity) | Sprint | QA | N/A | Improve SLA | FALSE | Timestamps | Group
49 | Planning & Estimation Discipline | Core | Planned vs Actual Time | Estimate vs actual | Phase 1 | Estimate vs actual | Sprint | PM | Aligned | Improve estimation | FALSE | Time logs | Compare
50 | Planning & Estimation Discipline | Core | Estimation Accuracy (%) | Accuracy KPI | Phase 1 | 1-¦A-E¦/E | Sprint | PM | >80% | Improve estimation | TRUE | Time logs | Compute
51 | Planning & Estimation Discipline | Supporting | Planned vs Actual Effort | Effort comparison | Phase 2 | SUM(E) vs SUM(A) | Sprint | PM | N/A | Improve capacity | FALSE | Time logs | Aggregate
52 | Planning & Estimation Discipline | Supporting | Overrun Ratio | Overrun measure | Phase 2 | A/E | Sprint | PM | <1.2 | Improve estimation | FALSE | Time logs | Ratio
53 | Planning & Estimation Discipline | Supporting | Underestimation Frequency | Underestimated tickets | Phase 2 | COUNT(A>E)/total | Sprint | PM | ↓ | Improve planning | FALSE | Time logs | Count
54 | Planning & Estimation Discipline | Core | Commitment Reliability (%) | Delivery reliability (=Sprint Completion Rate) | Phase 1 | Delivered/Committed | Sprint | PM | >90% | Improve planning | FALSE | Sprint baseline | Compare
55 | Planning & Estimation Discipline | Supporting | Scope Change Rate | Sprint scope changes | Phase 2 | Changed/total | Sprint | PM | ↓ | Stabilize | FALSE | Sprint logs | Track changes
56 | Planning & Estimation Discipline | Analytical | Scope Volatility Trend | Scope trend | Phase 3 | TREND(scope changes) | Sprint | PM | ↓ | Improve discipline | FALSE | Historical | Time series
57 | Planning & Estimation Discipline | Analytical | Re-prioritized Tickets | Priority changes | Phase 3 | COUNT(priority changes) | Sprint | PM | ↓ | Improve governance | FALSE | History | Track
58 | Planning & Estimation Discipline | Analytical | Repeated Carry-over | Repeated spillover | Phase 3 | COUNT(repeated carry) | Sprint | PM | 0 | Fix root cause | FALSE | Sprint history | Track
59 | Release Readiness | Indicator | Release Readiness Score | Release decision indicator | Phase 3 | Weighted score | Release | PMO | Ready | Go/No-Go | FALSE | Multiple metrics | Combine
60 | Release Readiness | Supporting | Testing Coverage (%) | Test coverage | Phase 2 | Tested/total | Sprint | QA | >90% | Improve QA | FALSE | Test data | Map
61 | Ticket Quality | Core | Missing Required Fields (%) | Missing fields | Phase 1 | Missing/total | Sprint | PMO | 0 | Enforce | FALSE | Fields | Check nulls
62 | Ticket Quality | Core | Tickets Without Updates (%) | Inactive tickets | Phase 1 | No update/active | Sprint | PMO | 0 | Follow up | TRUE | Last updated | Filter
63 | Ticket Quality | Supporting | Time Logging Completeness (%) | Logging quality | Phase 2 | Logged/expected | Sprint | PMO | 1 | Enforce logs | FALSE | Time logs | Compare
64 | Ticket Quality | Supporting | Description Quality Rate (%) | Description quality | Phase 2 | Weak/total | Sprint | PMO | ↓ | Improve | FALSE | Description | Audit
65 | Ticket Quality | Analytical | Status Inconsistency Rate | Workflow misuse | Phase 3 | Inconsistent/total | Sprint | PMO | 0 | Fix workflow | FALSE | Status logs | Detect invalid
66 | Delivery Health | Core | High-Priority Delivery Rate (%) | Percentage of high-priority (Immediate/Hotfix/Urgent) tickets delivered within their expected timeframe | Phase 1 | High-priority tickets completed on time / total high-priority tickets * 100 | Sprint | PM | ≥95% | Escalate delays immediately and prioritize critical work | TRUE | Priority, Due Date, Status, Close Date | Filter tickets with Priority in (Immediate, Hotfix, Urgent); check completion within due date or sprint boundary. On time = completed before Due Date.
67 | Execution Efficiency | Core | High-Priority Cycle Time | Average cycle time for high-priority tickets (In Progress → Done) | Phase 1 | AVG(close date - first In Progress date for high-priority tickets) | Daily | Dev Lead | ↓ (as low as possible) | Investigate delays in urgent work handling | TRUE | Priority, Status timestamps | Filter tickets with Priority in (Immediate, Hotfix, Urgent); compute time from first In Progress to Done
68 | Planning & Estimation Discipline | Core | Not Started (Count & %) | Committed tickets that never started during the sprint | Phase 1 | COUNT(Original Sprint = Sprint X AND never transitioned to In Progress) and Count / Planned Tickets * 100 | Sprint | PM | 0 or minimal | Review sprint planning and capacity assumptions | TRUE | Original Sprint, Status history | Use Original Sprint as commitment baseline; check tickets with no transition to In Progress during sprint
69 | Delivery Health | Core | Technical Debt (Count) | Unfinished committed tickets from previous sprints | Phase 1 | COUNT(Original Sprint < Current Sprint AND Status != Done/Closed) | Daily | PM | Downward trend | Prioritize debt reduction and review delivery capacity | TRUE | Original Sprint, Current Sprint, Status | Do not use Due Date; compare Original Sprint against current active sprint
70 | Delivery Health | Supporting | Technical Debt Ratio (%) | Technical debt as a percentage of all active tickets | Phase 2 | Technical Debt Tickets / Total Active Tickets * 100 | Sprint | PM | Downward trend | Control backlog growth and reduce accumulated commitments | FALSE | Original Sprint, Status | Total Active Tickets = all tickets not in Done/Closed across backlog and sprints
71 | Delivery Health | Analytical | Technical Debt Aging | Number of sprints a debt ticket has been delayed | Phase 3 | Current Sprint - Original Sprint | Sprint | PM | Low aging | Escalate old debt items and prioritize chronic delays | FALSE | Original Sprint, Current Sprint | Calculate sprint distance between committed sprint and current sprint
72 | Delivery Health | Supporting | New Debt Created | Committed tickets not completed by sprint end | Phase 2 | COUNT(Original Sprint = Sprint X AND Status != Done/Closed at Sprint End) | Sprint | PM | Low | Review sprint planning and unfinished causes | FALSE | Original Sprint, Status | Calculate at sprint closure before moving tickets forward
73 | Delivery Health | Supporting | Debt Burn-down | Debt tickets completed during the sprint | Phase 2 | COUNT(Original Sprint < Current Sprint AND closed during current sprint) | Sprint | PM | Upward trend | Ensure old commitments are being actively cleared | FALSE | Original Sprint, Status, Close Date | Filter tickets whose Original Sprint is older than current sprint and closed in current sprint
74 | Execution Efficiency | Analytical | Complexity-Normalized Cycle Time | Measures cycle time adjusted by ticket complexity to allow fair comparison across tickets | Phase 2 | Cycle Time / Complexity Weight | Sprint | Team Lead | Stable or decreasing | Investigate inefficiencies in handling low-complexity or medium-complexity tasks | FALSE | Status timestamps; Complexity Weight | Extract Cycle Time per ticket and divide by custom field "Complexity Weight" where value is 5, 8, 13, or 21
75 | Quality & Returns | Analytical | High Complexity Failure Rate (%) | Percentage of high-complexity tickets that result in returns | Phase 2 | COUNT(Returned tickets with Complexity Weight >= 13) / COUNT(Tickets with Complexity Weight >= 13) * 100 | Sprint | QA Lead | Low | Review design, implementation quality, and validation of complex tasks | TRUE | Complexity Weight; Return history | Filter tickets with Complexity Weight 13 or 21 and check whether they entered Returned status
76 | Bug Intelligence | Core | QA Escape Rate (%) | Percentage of bugs caused by issues that should have been caught during testing | Phase 2 | COUNT(Bugs where Bug Source = "Test Escape") / Total Bugs * 100 | Sprint | QA Lead | Low | Improve QA validation, checklist quality, and test execution | TRUE | Bug tracker; Bug Source | Filter Bug tracker items where Bug Source = "Test Escape"
77 | Bug Intelligence | Analytical | Test Coverage Gap Rate (%) | Percentage of bugs caused by missing test scenarios | Phase 2 | COUNT(Bugs where Bug Source = "Test Coverage Gap") / Total Bugs * 100 | Sprint | QA Lead | Low | Improve test case coverage and scenario design | FALSE | Bug tracker; Bug Source | Filter Bug tracker items where Bug Source = "Test Coverage Gap"
78 | Bug Intelligence | Analytical | Regression Rate (%) | Percentage of bugs caused by side effects or regressions | Phase 2 | COUNT(Bugs where Bug Source = "Side Effect / Regression") / Total Bugs * 100 | Sprint | Dev Lead | Low | Improve regression testing, code review, and impact analysis | TRUE | Bug tracker; Bug Source | Filter Bug tracker items where Bug Source = "Side Effect / Regression"
79 | Planning & Estimation Discipline | Analytical | Requirement Quality Issue Rate (%) | Percentage of bugs caused by design or requirement gaps | Phase 2 | COUNT(Bugs where Bug Source = "Design / Requirement Gap") / Total Bugs * 100 | Sprint | PM | Low | Improve requirement clarity, acceptance criteria, and design review | TRUE | Bug tracker; Bug Source | Filter Bug tracker items where Bug Source = "Design / Requirement Gap"
80 | Quality & Returns | Analytical | Critical Return Reason Rate (%) | Percentage of returns caused by serious development or implementation issues | Phase 2 | COUNT(Returns where Return Reason IN ("Wrong Implementation", "Caused Side Effect", "Code Quality Issue")) / Total Returns * 100 | Sprint | QA Lead | Low | Focus on reducing serious development mistakes and improving review quality | TRUE | Return Reason; Return history | Filter returned tickets by Return Reason and group critical reasons separately
81 | Execution Efficiency | Core | Sprint Logged Time | Total time logged during the reporting period on tickets belonging to the selected sprint | Phase 1 | SUM(Time Spent where Ticket Current Sprint = Sprint X AND Log Date within Period) | Daily / Sprint | Team Lead | Visible / controlled | Review sprint effort allocation and workload distribution | TRUE | Time logs; Sprint relation; Log date; User | Filter time entries by log date period and tickets related to the selected sprint
82 | Execution Efficiency | Core | Non-Sprint Logged Time | Total time logged during the reporting period on tickets outside the selected sprint scope | Phase 1 | SUM(Time Spent where Ticket Current Sprint != Sprint X AND Log Date within Period) | Daily / Sprint | Team Lead | Low / justified | Review out-of-sprint work and protect sprint focus | TRUE | Time logs; Sprint relation; Log date; User | Filter time entries by log date period and exclude tickets related to the selected sprint
83 | Planning & Estimation Discipline | Core | Out-of-Sprint Work Ratio (%) | Percentage of logged effort spent on work outside the selected sprint scope | Phase 1 | Non-Sprint Logged Time / (Sprint Logged Time + Non-Sprint Logged Time) * 100 | Sprint | PM | Low | Control scope leakage and review unplanned work | TRUE | Time logs; Sprint relation; Log date | Use time entries during sprint period and classify tickets as sprint vs non-sprint work
84 | Planning & Estimation Discipline | Analytical | PM vs Owner Estimation Variance (%) | Variance between PM estimation and ticket owner estimation | Phase 2 | ABS(PM Estimation - Owner Estimation) / PM Estimation * 100 | Sprint | PM | Low | Align PM and owner assumptions before sprint commitment | FALSE | PM Estimation; Owner Estimation | Compare both estimation fields at ticket level and aggregate by sprint, owner, or project
85 | Planning & Estimation Discipline | Analytical | Owner Estimation Accuracy (%) | Accuracy of owner estimation compared with actual time spent | Phase 2 | 1 - ABS(Actual Time Spent - Owner Estimation) / Owner Estimation | Sprint | Team Lead | High | Improve owner-level estimation discipline and calibration | FALSE | Owner Estimation; Time Spent | Compare owner estimate to total logged time for the ticket or selected period
86 | Planning & Estimation Discipline | Supporting | Carry-over Reason Distribution | Distribution of carry-over tickets by reason category | Phase 2 | COUNT(Carry-over Tickets) grouped by Carry-over Reason | Sprint | PM | N/A | Identify dominant causes of carry-over and corrective actions | FALSE | Original Sprint; Current Sprint; Carry-over Reason; Status | Filter tickets carried over from original sprint and group by carry-over reason field
87 | Execution Efficiency | Analytical | Work Intensity Ratio (%) | Ratio of actual time spent to calendar duration for a ticket or group of tickets | Phase 2 | Total Time Spent / Calendar Duration * 100 | Sprint / Period | Team Lead | Balanced | Investigate low work density, waiting time, or execution fragmentation | FALSE | Time logs; Start date; Due/Close date; Status timestamps | Calculate ticket or group calendar duration and compare with total logged effort

## Metrics-Phase Matrix
Category | Phase 1 | Phase 2 | Phase 3
Delivery Health | Completed Committed Tickets; Sprint Completion Rate (%); Planned Tickets; Carry-over (%); Throughput; High-Priority Delivery Rate (%); Technical Debt (Count); Sprint Status | Carry-over Trend; Delivery Predictability (%); Milestone Deliverables; Technical Debt Ratio (%); New Debt Created; Debt Burn-down | Milestone Completion (%); Technical Debt Aging
Execution Efficiency | Cycle Time; High-Priority Cycle Time; Blocked Tickets Count; Blocked Duration; Ticket Idle Time; Sprint Logged Time; Non-Sprint Logged Time | Lead Time; Overdue Tickets; Overdue Duration; Time in Status; Integration Time; Active Dev Time; Avg Dev Time per Ticket; Tickets Stuck in Status; Complexity-Normalized Cycle Time; Work Intensity Ratio (%) | Work-in-Progress (WIP); Bottleneck Stage
Quality & Returns | Return Rate (%); Rework Ratio (%); Total Rework Time; First-Time Pass Rate (%) | Returns per Ticket; Avg Returns per Ticket; Return-Induced Dev Time; QA Fail Rate (%); Validation Rejection Rate (%); Return Trend; Return Reasons Distribution; High Complexity Failure Rate (%); Critical Return Reason Rate (%) | Return Loop Depth; Return Cycle Duration; High-return Tickets; Return-based Fail Rate (%)
Bug Intelligence | Bugs Created; Bugs Resolved; Bug Leakage (%); Critical Bugs Open | Bug Backlog Trend; Bug Reopen Rate; Severity Distribution; QA Escape Rate (%); Test Coverage Gap Rate (%); Regression Rate (%) | Open Critical Bug Aging; Resolution Time by Severity
Planning & Estimation Discipline | Planned vs Actual Time; Estimation Accuracy (%); Commitment Reliability (%); Not Started (Count & %); Out-of-Sprint Work Ratio (%) | Planned vs Actual Effort; Overrun Ratio; Underestimation Frequency; Scope Change Rate; Requirement Quality Issue Rate (%); PM vs Owner Estimation Variance (%); Owner Estimation Accuracy (%); Carry-over Reason Distribution | Scope Volatility Trend; Re-prioritized Tickets; Repeated Carry-over
Release Readiness | — | Testing Coverage (%) | Release Readiness Score
Ticket Quality | Missing Required Fields (%); Tickets Without Updates (%) | Time Logging Completeness (%); Description Quality Rate (%) | Status Inconsistency Rate

## Cross-Metrics
Cross-Metric Name | Components | Insight | Usage
Cycle Time vs Complexity Weight | Cycle Time + Complexity Weight | Determines whether higher complexity is properly reflected in delivery time | Evaluate estimation logic and planning maturity
Rework Ratio by Developer | Rework Ratio (%) + Assignee | Identifies developers producing unstable outputs | Coaching, performance evaluation
Returns Distribution by Module / Feature | Return Rate (%) + Module/Page | Detects unstable product areas | Product quality improvement, root cause analysis
Bug Leakage vs Return Rate | Bug Leakage (%) + Return Rate (%) | Distinguishes whether quality problems are caught internally or escape as bugs | Balance QA vs Dev improvements
Bottleneck Stage Analysis | Time in Status + Tickets Stuck in Status | Identifies where workflow slows down | Detect bottlenecks (Dev, QA, Review, Merge)
Estimation Accuracy vs Carry-over | Estimation Accuracy (%) + Carry-over (%) | Determines if planning inaccuracies drive delivery failures | Improve sprint planning and estimation
WIP vs Cycle Time | WIP + Cycle Time | Evaluates impact of workload on delivery speed | Prevent team overloading
Cycle Time vs Return Rate | Cycle Time + Return Rate (%) | Identifies trade-off between speed and quality | Balance speed vs quality
Flow Efficiency (%) | Active Dev Time / Lead Time | Measures productive vs total time | Identify waste and delays
QA Effectiveness Index | 1 - (Post-Integration Bugs / Total Bugs), and Count of Bug Source (Test Escape or Coverage Gap) | Measures effectiveness of QA in catching defects early | Improve QA process
Release Risk Score | Critical Bugs Open + Return Rate (%) + Testing Coverage (%) + Sprint Completion Rate (%) | Evaluates overall release readiness risk | Go/No-Go decision support
Workload vs Rework | WIP + Rework Ratio (%) | Detects if overload reduces quality | Capacity planning
Delivery vs Capacity | Throughput + WIP | Detects utilization and delivery balance against available capacity | Optimize team utilization and delivery balance
High-Priority Responsiveness | High-Priority Delivery Rate (%) + High-Priority Cycle Time | Evaluates system responsiveness to urgent business needs | Ensure critical issues are handled with priority and speed
Technical Debt Pressure | Technical Debt (Count) + Throughput + Debt Burn-down | Evaluates whether the team is reducing or accumulating unfinished commitments | Control long-term delivery sustainability
Planning Failure Signal | Not Started (Count & %) + Carry-over (%) | Combines not-started work and carry-over to identify planning weakness | Improve sprint planning discipline
QA vs Dev Responsibility Balance | QA Escape Rate (%) + Critical Return Reason Rate (%) + Return Reasons Distribution | Separates quality issues caused by missed QA detection from issues caused by development or implementation problems | Balance QA process improvement with developer coaching and code quality actions
Complexity vs Quality | Complexity Weight + High Complexity Failure Rate (%) + Return Rate (%) + Bug Leakage (%) | Identifies whether complex tickets are disproportionately causing returns, bugs, or escaped defects | Improve planning, review, and testing strategy for high-complexity work
Regression Risk Indicator | Regression Rate (%) + Return Loop Depth + Bug Leakage (%) | Identifies whether system instability is increasing due to side effects and repeated rework | Strengthen regression testing, code review, and impact analysis before release

## Dashboard Tables Inventory
Table ID | Dashboard Page | Table Name | Purpose | Primary Metrics Supported | Required Fields | Main Filters | Diagrams/Charts Needed | Report Mode | Reuse / Cross View | Other Dashboards that Use this Table as Supporting Tab | Notes for Developer
T01 | PMO Control Dashboard | Open Technical Tickets Snapshot | Show open technical workload and distribution by project. | Open Technical Tickets; Blocked Tickets Count | Project; Tracker; Status; Ticket Owner; Priority | Project; Tracker; Status; Date | KPI cards; stacked bar by status/project | State at Specific Date | Primary |  | Technical tickets include Bug, Feature, and Change Request / Improvement.
T02 | PMO Control Dashboard | Cross-Project Risk Summary | Summarize project/sprint health and risk signals. | Sprint Status; Sprint Completion Rate; Carry-over; Technical Debt; Blocked Tickets; Critical Bugs; Return Rate; Missing Fields | Project; Sprint; Status; Original Sprint; Return history; Bug severity | Project; Sprint; Date | KPI cards; risk heatmap/table; conditional formatting | State at Specific Date | Primary |  | Use consistent color and risk logic.
T03 | PMO Control Dashboard | Open Tasks / Business Jobs | Track non-technical open business work. | Open Tasks; Business Jobs | Project; Tracker; Status; Owner | Project; Tracker; Status | Summary table; status distribution chart | State at Specific Date | Primary |  | Keep separate from technical ticket metrics.
T04 | PMO Control Dashboard | Open Milestones | Show milestone progress and risk. | Milestone Deliverables; Milestone Completion (%) | Project; Milestone; Status; Due Date | Project; Milestone; Date | Milestone progress bar; risk indicator | State at Specific Date | Primary |  | Use milestone-linked tickets and status.
T05 | Sprint Delivery Dashboard | Committed Tickets for Sprint #X | Provide retrospective baseline for sprint metrics. | Planned Tickets; Completed Committed Tickets; Sprint Completion Rate; Carry-over; Not Started; Technical Debt | Original Sprint; Current Sprint; Status; Owner; Priority; Start/Due Date; Estimate; Spent Time; Carry-over Reason | Project; Sprint; Original Sprint; Owner; Priority; Status | Detailed drill-down table; status/owner filters | State at Specific Date | Primary |  | Must be retrospectively available and must preserve Original Sprint.
T06 | Sprint Delivery Dashboard | Sprint Tasks Distribution in Statuses | Show sprint work distribution by status and owner. | WIP; Blocked Tickets; Sprint Status | Sprint relation; Status; Owner | Sprint; Owner; Status | Owner-by-status matrix; stacked bar WIP/Stopped/Done | State at Specific Date | Primary |  | Include WIP, Stopped, and Done grouped subtotals.
T07 | Sprint Delivery Dashboard | Sprint Execution Efficiency / Original Sprint Composition | Compare current sprint vs carried-over work. | Carry-over (%); Technical Debt Count; Planned Tickets | Original Sprint; Current Sprint; Status | Sprint; Original Sprint | Pie or stacked bar: current vs carried-over scope | State at Specific Date | Primary |  | Split current-sprint tickets from carried-over tickets.
T08 | Sprint Delivery Dashboard | Sprint Completion Summary | Summarize completion, unfinished work, and sprint health. | Completed Committed Tickets; Sprint Completion Rate; Carry-over; Sprint Status | Original Sprint; Sprint; Status; Close Date | Project; Sprint | KPI cards; completion/carry-over progress bar | State at Specific Date | Primary |  | Use sprint-end snapshot for accurate completion.
T09 | Sprint Delivery Dashboard | Done Tickets Time Efficiency | Show cycle time and lead time for completed tickets. | Cycle Time; Lead Time | Created Date; First In Progress Timestamp; Close Date | Project; Sprint; Owner | Cycle/lead time bar chart or distribution | Periodic Report | Supporting detail | Sprint Delivery Dashboard; Team / Ticket Owner Performance Dashboard; Time Utilization & Scope Control Dashboard | Requires reliable workflow timestamps.
T10 | Sprint Delivery Dashboard | Ticket Status Change Trend | Track status movement over a reporting period. | Throughput; Time in Status; Tickets Stuck in Status | Status history; Date | Project; Period; Status | Line chart/trend table by status over period | Trend / Flow Report | Supporting flow view | PMO Control Dashboard; Sprint Delivery Dashboard; QA & Returns Dashboard | Compare start/end of period and intermediate dates.
T11 | Sprint Delivery Dashboard | Tracker Change Trend | Track tracker-level movement over a reporting period. | Bugs Created; Bugs Resolved; Throughput | Tracker; Status; Date | Project; Period; Tracker | Line chart/trend table by tracker over period | Trend / Flow Report | Supporting flow view | Sprint Delivery Dashboard; Bug Control Dashboard | Useful for Bug, Change Request, Feature, and Customer Support flow.
T12 | Sprint Delivery Dashboard | High-Priority Delivery View | Track urgent work completion and cycle time. | High-Priority Delivery Rate; High-Priority Cycle Time | Priority; Status; First In Progress; Close Date | Project; Sprint; Priority | KPI cards; high-priority delivery bar/table | Periodic Report | Primary |  | Use approved high-priority labels only.
T13 | Team / Ticket Owner Performance Dashboard | Ticket Delivery Analysis by Owner | Compare owner-level commitment, completion, debt, and throughput. | Completed Committed Tickets; Throughput; Technical Debt Count; Commitment Reliability | Owner; Original Sprint; Status; Close Date; Due Date | Project; Sprint; Owner | Owner summary table; bar chart by owner | Periodic Report | Primary |  | Balanced owner-level delivery view.
T14 | Team / Ticket Owner Performance Dashboard | Done Committed Tickets Analysis by Owner | Analyze completed work by owner, complexity, returns, and cycle time. | Cycle Time; High-Priority Cycle Time; Return Rate; Complexity Weight | Owner; Complexity Weight; Return history; Status timestamps | Project; Sprint; Owner | Owner comparison table; cycle/returns bar chart | Periodic Report | Primary |  | Do not use completed count alone for performance judgment.
T15 | Team / Ticket Owner Performance Dashboard | Average Time for Each Status | Identify owner/team bottlenecks by workflow status. | Time in Status; Bottleneck Stage | Status history; Owner | Project; Sprint; Owner; Status | Heatmap or bar chart for average time in status | Periodic Report | Supporting detail | Sprint Delivery Dashboard; Team / Ticket Owner Performance Dashboard; Time Utilization & Scope Control Dashboard | Requires status transition timestamps.
T16 | Team / Ticket Owner Performance Dashboard | Owner Ticket Idle / No Update Detail | Identify owner-level stale or inactive work. | Ticket Idle Time; Tickets Without Updates (%) | Owner; Last Update; Status | Project; Owner; Status | Aging table; conditional formatting for idle days | State at Specific Date | Primary |  | Flag active tickets with no recent update.
T17 | Team / Ticket Owner Performance Dashboard | Owner Time Allocation | Show sprint vs non-sprint logged time by owner. | Sprint Logged Time; Non-Sprint Logged Time; Out-of-Sprint Work Ratio | Time logs; User; Activity; Ticket ID; Sprint relation | Project; Sprint; Period; User | Stacked bar sprint vs non-sprint time by owner | Periodic Report | Secondary cross-view | Time Utilization & Scope Control Dashboard | Show sprint vs non-sprint logged time by owner. This table is identical to T42 and is reused here as a secondary cross-view.
T18 | QA & Returns Dashboard | Done Tickets Analysis | Compare returned vs no-return completed tickets. | Return Rate; First-Time Pass Rate | Status; Return Count; Close Date | Project; Sprint; Period | Returned vs no-return pie/bar chart | Periodic Report | Primary |  | Base table for first-time pass analysis.
T19 | QA & Returns Dashboard | Returned Tickets Analysis — Count | Count returns by return type. | Returns per Ticket; Return Rate | Return Type; Return events | Project; Sprint; Return Type | Return count bar chart by return type | Periodic Report | Primary |  | Requires reliable return-loop tracking.
T20 | QA & Returns Dashboard | Returned Tickets Analysis — Duration | Analyze rework duration by type. | Total Rework Time; Return-Induced Dev Time | Time logs; Return states; Return type | Project; Sprint; Return Type | Rework duration bar chart by return type | Periodic Report | Primary |  | Use time logs and return transition timestamps.
T21 | QA & Returns Dashboard | Work & Rework Ratio | Compare total work duration and rework duration. | Rework Ratio; Total Rework Time | Time logs; Return state; Work type | Project; Sprint; Period | Work vs rework ratio chart | Periodic Report | Primary |  | Supports quality cost analysis.
T22 | QA & Returns Dashboard | Return Reason Analysis | Analyze returns by standardized reason. | Return Reasons Distribution; Critical Return Reason Rate | Return Reason; Return events | Project; Sprint; Return Reason | Return reason distribution bar/pie chart | Periodic Report | Primary |  | Uses custom field Return Reason.
T23 | Bug Control Dashboard | Bugs Analysis by Category | Track bugs by source/category across period states. | Bugs Created; Bugs Resolved; Bug Backlog Trend; Bug Source metrics | Bug Source; Created Date; Close Date; Status | Project; Period; Bug Source | Bug source/category trend table; bar chart | Periodic Report | Primary |  | Uses custom field Bug Source.
T24 | Bug Control Dashboard | Bug Impact Summary | Summarize bug impact rating across beginning/found/closed/remaining. | Critical Bugs Open; Severity Distribution | Bug Impact Rating; Severity; Status | Project; Period; Severity | Bug impact summary KPI/table | Periodic Report | Primary |  | Impact rating can support severity when severity is incomplete.
T25 | Bug Control Dashboard | Related Page Histogram | Identify modules/pages with concentrated bugs. | Bugs by Module/Page; Bug Count | Bug Related Page / Module; Bug Source; Status | Project; Period; Page/Module | Histogram/bar chart by page/module | Periodic Report | Primary |  | Group bugs by affected page/module.
T26 | Bug Control Dashboard | Critical Bugs Open Detail | List critical open bugs requiring action. | Critical Bugs Open; Open Critical Bug Aging | Severity/Priority; Status; Created Date; Owner | Project; Severity; Status | Critical bug detail table with risk coloring | State at Specific Date | Primary |  | Immediate triage list for release risk.
T27 | Planning & Estimation Dashboard | Planning vs Actual Time Analysis | Compare estimated time and actual spent time. | Planned vs Actual Time; Estimation Accuracy | Estimated Time; Time logs; Sprint | Project; Sprint; Owner | Variance table; estimate vs actual bar chart | Periodic Report | Primary |  | Compare estimate with time spent during sprint period.
T28 | Planning & Estimation Dashboard | PM Estimation vs Owner Estimation vs Time Spent | Identify planning and estimation variance. | PM vs Owner Estimation Variance; Owner Estimation Accuracy | PM Estimation; Owner Estimation; Time logs | Project; Sprint; Owner | Variance table; PM/Owner/Actual comparison chart | Periodic Report | Primary |  | Requires Owner Estimation field.
T29 | Planning & Estimation Dashboard | Original Sprint Composition | Split current sprint work vs carried-over work. | Carry-over; Technical Debt Count | Original Sprint; Current Sprint; Status | Project; Sprint; Original Sprint | Current vs carried-over composition chart | State at Specific Date | Primary |  | Shows planning stability and spillover.
T30 | Planning & Estimation Dashboard | Open Planned Tickets Health | Identify missing owner, dates, and estimation on planned work. | Missing Required Fields; Tickets Missing Owner; Tickets Missing Estimation | Owner; Start Date; Due Date; PM Estimation; Status | Project; Status; Tracker | Missing-field summary table; data quality indicators | State at Specific Date | Reused table | Ticket Quality & Data Discipline Dashboard | Also reused by Ticket Quality.
T31 | Planning & Estimation Dashboard | Not Started Tickets | List committed tickets never started. | Not Started (Count & %) | Original Sprint; Status history; First In Progress timestamp | Project; Sprint; Owner | Not-started detail table by owner/priority | State at Specific Date | Primary |  | Detect committed work that never entered In Progress.
T32 | Planning & Estimation Dashboard | Commitment Reliability Summary | Track planned vs done, carry-over, and not-started by sprint. | Commitment Reliability; Sprint Completion Rate; Carry-over; Not Started | Original Sprint; Status; Close Date | Project; Sprint | Sprint reliability trend/table | Periodic Report | Primary |  | Shows planning reliability by sprint.
T33 | Planning & Estimation Dashboard | Carry-over Reason Analysis | Identify reasons for moved / unfinished work. | Carry-over Reason Distribution | Carry-over Reason; Original Sprint; Status | Project; Sprint; Reason | Carry-over reason distribution chart | Periodic Report | Primary |  | Requires controlled Carry-over Reason values.
T34 | Ticket Quality & Data Discipline Dashboard | Open Planned Tickets Health | Show planning-field completeness. | Missing Required Fields; Tickets Missing Owner; Tickets Missing Estimation | Owner; Start Date; Due Date; PM Estimation; Priority | Project; Status; Tracker | Missing-field summary table; data-quality indicators | State at Specific Date | Reused table | Planning & Estimation Dashboard | Same source concept as T30, used for data discipline.
T35 | Ticket Quality & Data Discipline Dashboard | Tickets Without Updates | Identify stale active tickets. | Tickets Without Updates; Ticket Idle Time | Last Update; Status; Owner | Project; Owner; Status | Inactive tickets table; aging conditional formatting | State at Specific Date | Primary |  | Use inactivity threshold.
T36 | Ticket Quality & Data Discipline Dashboard | Missing Required Fields Detail | List tickets missing required planning fields. | Missing Required Fields (%) | Owner; Start Date; Due Date; Estimation; Priority; Sprint | Project; Status; Tracker | Missing-required-fields drill-down table | State at Specific Date | Primary |  | Drill-down table for missing-field KPI.
T37 | Ticket Quality & Data Discipline Dashboard | Data Reliability by Project | Summarize data quality by project. | Missing Required Fields; Tickets Without Updates; Time Logging Completeness | Project; Required fields; Last Update; Time logs | Project; Period | Data reliability by project scorecard | State at Specific Date | Primary |  | Used to judge dashboard confidence.
T38 | Time Utilization & Scope Control Dashboard | Spent Time: General vs Sprint Tickets | Compare sprint and non-sprint logged effort. | Sprint Logged Time; Non-Sprint Logged Time; Out-of-Sprint Work Ratio | Time logs; Ticket ID; Sprint relation; User; Log Date | Project; Sprint; Period; User | Stacked bar: sprint vs non-sprint time | Periodic Report | Primary |  | Separates effort spent inside vs outside sprint scope.
T39 | Time Utilization & Scope Control Dashboard | Out-of-Sprint Scope Works | Identify time logs on tickets outside sprint scope. | Non-Sprint Logged Time; Out-of-Sprint Work Ratio | Time logs; Ticket ID; Sprint relation; Activity | Project; Sprint; Period; User | Out-of-sprint work detail table | Periodic Report | Primary |  | Shows out-of-sprint tickets/activities by owner.
T40 | Time Utilization & Scope Control Dashboard | Spent Time on Group of Tickets in Specific Date Period | Analyze period-specific effort by ticket and owner. | Sprint Logged Time; Non-Sprint Logged Time; Time Spent by Owner | Time logs; User; Activity; Ticket ID; Log Date; Sprint relation | Project; Sprint; Period; User | Spent-time detail table; period comparison | Periodic Report | Primary |  | Includes previous logged time and time logged during selected period.
T41 | Time Utilization & Scope Control Dashboard | Average Spent Time vs Calendar Duration | Compare actual effort with calendar duration. | Work Intensity Ratio | Time logs; Start Date; Due/Close Date; Status timestamps | Project; Sprint; Owner; Period | Scatter/table: spent time vs calendar duration | Periodic Report | Primary |  | Detects low work density, waiting time, or fragmented execution.
T42 | Time Utilization & Scope Control Dashboard | Owner Time Allocation | Summarize sprint/non-sprint time by owner. | Sprint Logged Time; Non-Sprint Logged Time; Out-of-Sprint Work Ratio | Time logs; User; Sprint relation; Activity | Project; Sprint; Period; User | Stacked bar sprint vs non-sprint time by owner | Periodic Report | Primary; reused by Team / Ticket Owner Performance Dashboard | Team / Ticket Owner Performance Dashboard | Primary Time Utilization table for sprint vs non-sprint logged time by owner.
T43 | Time Utilization & Scope Control Dashboard | Activity Distribution in Spent Time Report | Show logged time distribution by activity type during the selected period. | Sprint Logged Time; Non-Sprint Logged Time; Out-of-Sprint Work Ratio | Time logs; User; Activity; Ticket ID; Sprint relation; Log date | Project; Sprint; Period; User; Activity | Activity distribution bar/pie chart | Periodic Report | Primary |  | Group time entries by activity type and separate sprint vs non-sprint logged time.
T44 | PMO Control Dashboard | Feature / Improvement Visibility by Version or Date | Track Features and Improvements by version/date, status, owner, and sprint. | Throughput; Planned Tickets; Sprint Status | Tracker; Version/Target Version; Created Date; Due Date; Status; Owner; Sprint | Project; Version; Date range; Tracker; Status; Owner | Feature/improvement table by version/date; optional timeline | State at Specific Date / Periodic Report | Primary |  | Filter tracker to Feature and Change Request / Improvement and group by target version or reporting date.
T45 | Sprint Delivery Dashboard | Daily Agile Board Snapshot | Capture daily sprint board status counts for retrospective sprint-flow analysis. | Sprint Status; WIP; Blocked Tickets Count; Throughput; Ticket Status Change Trend | Sprint; Status; Snapshot Date; Owner; Tracker | Project; Sprint; Snapshot Date; Status; Owner | Daily board snapshot table; stacked trend chart by status | State at Specific Date / Trend Report | Primary |  | Store or extract daily status counts during the sprint to allow retrospective board snapshots.

## Dashboard Tables Hierarchy
Dashboard Section | Section Purpose | Table ID | Table Name | Table Role / Note
PMO Control Dashboard | Executive and PMO-level visibility across projects, sprints, risks, delivery health, blockers, quality signals, and management control indicators. | T01 | Open Technical Tickets Snapshot | Primary table
PMO Control Dashboard | Executive and PMO-level visibility across projects, sprints, risks, delivery health, blockers, quality signals, and management control indicators. | T02 | Cross-Project Risk Summary | Primary table
PMO Control Dashboard | Executive and PMO-level visibility across projects, sprints, risks, delivery health, blockers, quality signals, and management control indicators. | T03 | Open Tasks / Business Jobs | Primary table
PMO Control Dashboard | Executive and PMO-level visibility across projects, sprints, risks, delivery health, blockers, quality signals, and management control indicators. | T04 | Open Milestones | Primary table
PMO Control Dashboard | Executive and PMO-level visibility across projects, sprints, risks, delivery health, blockers, quality signals, and management control indicators. | T44 | Feature / Improvement Visibility by Version or Date | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T05 | Committed Tickets for Sprint #X | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T06 | Sprint Tasks Distribution in Statuses | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T07 | Sprint Execution Efficiency / Original Sprint Composition | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T08 | Sprint Completion Summary | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T09 | Done Tickets Time Efficiency | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T10 | Ticket Status Change Trend | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T11 | Tracker Change Trend | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T12 | High-Priority Delivery View | Primary table
Sprint Delivery Dashboard | Sprint commitment, completion, carry-over, status distribution, delivery speed, high-priority delivery, and sprint flow. | T45 | Daily Agile Board Snapshot | Primary table
Team / Ticket Owner Performance Dashboard | Balanced owner-level visibility across commitment, completion, throughput, cycle time, returns, idle work, and time allocation. | T13 | Ticket Delivery Analysis by Owner | Primary table
Team / Ticket Owner Performance Dashboard | Balanced owner-level visibility across commitment, completion, throughput, cycle time, returns, idle work, and time allocation. | T14 | Done Committed Tickets Analysis by Owner | Primary table
Team / Ticket Owner Performance Dashboard | Balanced owner-level visibility across commitment, completion, throughput, cycle time, returns, idle work, and time allocation. | T15 | Average Time for Each Status | Primary table
Team / Ticket Owner Performance Dashboard | Balanced owner-level visibility across commitment, completion, throughput, cycle time, returns, idle work, and time allocation. | T16 | Owner Ticket Idle / No Update Detail | Primary table
Team / Ticket Owner Performance Dashboard | Balanced owner-level visibility across commitment, completion, throughput, cycle time, returns, idle work, and time allocation. | T17 | Owner Time Allocation | Secondary/cross-view; primary source is T42 under Time Utilization & Scope Control Dashboard
QA & Returns Dashboard | Internal quality, return loops, rework volume, first-time pass behavior, return reasons, and rework duration. | T18 | Done Tickets Analysis | Primary table
QA & Returns Dashboard | Internal quality, return loops, rework volume, first-time pass behavior, return reasons, and rework duration. | T19 | Returned Tickets Analysis — Count | Primary table
QA & Returns Dashboard | Internal quality, return loops, rework volume, first-time pass behavior, return reasons, and rework duration. | T20 | Returned Tickets Analysis — Duration | Primary table
QA & Returns Dashboard | Internal quality, return loops, rework volume, first-time pass behavior, return reasons, and rework duration. | T21 | Work & Rework Ratio | Primary table
QA & Returns Dashboard | Internal quality, return loops, rework volume, first-time pass behavior, return reasons, and rework duration. | T22 | Return Reason Analysis | Primary table
Bug Control Dashboard | Bug creation, closure, backlog movement, bug source/category, impact, critical bugs, and affected pages/modules. | T23 | Bugs Analysis by Category | Primary table
Bug Control Dashboard | Bug creation, closure, backlog movement, bug source/category, impact, critical bugs, and affected pages/modules. | T24 | Bug Impact Summary | Primary table
Bug Control Dashboard | Bug creation, closure, backlog movement, bug source/category, impact, critical bugs, and affected pages/modules. | T25 | Related Page Histogram | Primary table
Bug Control Dashboard | Bug creation, closure, backlog movement, bug source/category, impact, critical bugs, and affected pages/modules. | T26 | Critical Bugs Open Detail | Primary table
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T27 | Planning vs Actual Time Analysis | Primary table
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T28 | PM Estimation vs Owner Estimation vs Time Spent | Primary table
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T29 | Original Sprint Composition | Primary table
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T30 | Open Planned Tickets Health | Reused table concept across Planning and Ticket Quality
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T31 | Not Started Tickets | Primary table
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T32 | Commitment Reliability Summary | Primary table
Planning & Estimation Dashboard | Planning reliability, estimation accuracy, commitment realism, not-started work, carry-over reasons, and planned vs actual effort. | T33 | Carry-over Reason Analysis | Primary table
Ticket Quality & Data Discipline Dashboard | Ticket completeness, update discipline, required-field quality, and reliability of dashboard source data. | T34 | Open Planned Tickets Health | Reused table concept across Planning and Ticket Quality
Ticket Quality & Data Discipline Dashboard | Ticket completeness, update discipline, required-field quality, and reliability of dashboard source data. | T35 | Tickets Without Updates | Primary table
Ticket Quality & Data Discipline Dashboard | Ticket completeness, update discipline, required-field quality, and reliability of dashboard source data. | T36 | Missing Required Fields Detail | Primary table
Ticket Quality & Data Discipline Dashboard | Ticket completeness, update discipline, required-field quality, and reliability of dashboard source data. | T37 | Data Reliability by Project | Primary table
Time Utilization & Scope Control Dashboard | Logged effort, sprint vs non-sprint work, out-of-sprint activity, owner time allocation, activity distribution, and work-density indicators. | T38 | Spent Time: General vs Sprint Tickets | Primary table
Time Utilization & Scope Control Dashboard | Logged effort, sprint vs non-sprint work, out-of-sprint activity, owner time allocation, activity distribution, and work-density indicators. | T39 | Out-of-Sprint Scope Works | Primary table
Time Utilization & Scope Control Dashboard | Logged effort, sprint vs non-sprint work, out-of-sprint activity, owner time allocation, activity distribution, and work-density indicators. | T40 | Spent Time on Group of Tickets in Specific Date Period | Primary table
Time Utilization & Scope Control Dashboard | Logged effort, sprint vs non-sprint work, out-of-sprint activity, owner time allocation, activity distribution, and work-density indicators. | T41 | Average Spent Time vs Calendar Duration | Primary table
Time Utilization & Scope Control Dashboard | Logged effort, sprint vs non-sprint work, out-of-sprint activity, owner time allocation, activity distribution, and work-density indicators. | T42 | Owner Time Allocation | Primary table; reused as T17 in Team / Ticket Owner Performance Dashboard
Time Utilization & Scope Control Dashboard | Logged effort, sprint vs non-sprint work, out-of-sprint activity, owner time allocation, activity distribution, and work-density indicators. | T43 | Activity Distribution in Spent Time Report | Primary table